Daily Project Progress Report

Internal Team Report | Confidential

Project Information

| Project Name | FBR Z - E-Invoicing Portal | Report Date | 08/05/2026 |
| --- | --- | --- | --- |
| Client | FBR / PRAL | Reporting Period | Day 3 |
| Project Manager | Dawood Arqam | Overall Status | On Track |
| Technology Stack | React, TypeScript/Express, Prisma, PostgreSQL | Environment | Local + Mocked FBR APIs |

Progress Summary

| Total Deliverables | Completed | In Progress | Pending / Blocked |
| --- | --- | --- | --- |
| 13 | 11 | 1 | 1 |

Client Deliverables

Deliverables tracked against the FBR DI guide, backend logic document, and team proposal.

| # | Deliverable | Description / Client Requirement | Status | Priority |
| --- | --- | --- | --- | --- |
| 1 | Database & Infrastructure | Prisma + PostgreSQL schema, database sync, core models and cleanup | Done | High |
| 2 | Token Management | Token save/status flow through /api/token with secure backend storage | Done | High |
| 3 | Guide-Compatible APIs | Route aliases for token, ref, invoice, products, queue, sandbox, dashboard | Done | High |
| 4 | Invoice Submission | New Invoice/InvoiceItem flow with failed submission logging and mapped errors | Done | High |
| 5 | Offline Queue | Auto processing, retry endpoints, failed state, 20-hour warning and 24-hour deadline | Done | High |
| 6 | Sandbox Certification | Required scenarios, results/summary/status, mock run coverage and eligibility flag | Done | High |
| 7 | Reference Data | Guide-compatible /api/ref routes and required query parameter aliases | Done | Medium |
| 8 | Rule 150R Print/PDF | QR v2 at 1 inch, required invoice fields, watermark and FBR DI logo | Done | High |
| 9 | Frontend Error Display | Structured backend/FBR errors shown near affected invoice fields/items | Done | Medium |
| 10 | Company Profile | Company profile saved in DB and seller details pre-filled on invoice form | Done | Medium |
| 11 | Dashboard Chart | Chart API function and frontend wiring started; final UI/testing pending | In Progress | Medium |
| 12 | Frontend Filters | Dashboard and invoice list date/status/type filters still pending | Pending | Medium |
| 13 | Live FBR Testing | Sandbox/live validation pending PRAL sandbox token | Blocked | High |

Work Completed Today

Tasks completed or progressed during today's local implementation session.

| # | Area | Task / Activity Completed | Status | % Done |
| --- | --- | --- | --- | --- |
| 1 | Backend Route Aliases | Confirmed/fixed guide-compatible backend aliases for /api/token, /api/ref, /api/invoice, /api/invoices, /api/products, /api/queue, /api/sandbox and /api/dashboard. | Done | 100% |
| 2 | Reference API Tightening | Verified /api/ref/* names and query parameter aliases against documentation, including HS codes, UOM, SRO, rates and registration type routes. | Done | 100% |
| 3 | Failed Invoice Logging | Improved failed FBR submission persistence with FAILED status, raw FBR response, mapped error code, timestamp and invoice snapshot. | Done | 100% |
| 4 | Frontend Error Display | Updated structured FBR error display so mapped backend errors appear clearly beside affected invoice fields and line items. | Done | 100% |
| 5 | Mocked Invoice Flow Test | Added/verified local mocked end-to-end invoice flow coverage for submit failure, mapped error saving and frontend display. | Done | 100% |
| 6 | Offline Queue Flow Test | Added/verified mocked offline queue flow for add, process, retry, failed state, uploaded state and 20/24-hour timing flags. | Done | 100% |
| 7 | AddInvoice Auto-Enqueue | Verified and wired offline/network-failure invoice creation to enqueue automatically instead of losing invoice data. | Done | 100% |
| 8 | Rule 150R Print/QR | Verified/tightened PDF print/download flow: QR version 2, 72pt/1 inch size, item tax/SRO fields, offline watermark and shared print/download generator. | Done | 100% |
| 9 | DashboardSlice URL Fix | Removed hardcoded fbrdashboard.techionik.com API URLs and switched the Redux slice to local backend base URL. | Done | 100% |
| 10 | Sandbox Run Test | Added mocked sandbox run test for single scenario, all required scenarios, results, summary and eligibleForProduction flag. | Done | 100% |
| 11 | Company Profile Prefill | AddInvoice now loads company profile and pre-fills seller NTN/CNIC, business name, province and address. | Done | 100% |
| 12 | FBR DI Logo in PDF | Converted/cropped the supplied FBR DI logo source and embedded the selected PNG in the invoice PDF header. | Done | 100% |
| 13 | Deprecated DB Cleanup | Confirmed Prisma/PostgreSQL is required by docs, verified legacy InvoiceRecord rows were already migrated, dropped deprecated InvoiceRecord and OfflineInvoiceQueue models/tables, then regenerated Prisma client. | Done | 100% |
| 14 | Dashboard Chart | Installed Recharts and started frontend chart integration using /api/dashboard/charts; final rendering and verification still pending. | In Progress | 60% |

Blockers & Issues

| Blocker / Issue | Impact | Action / Owner | ETA to Resolve |
| --- | --- | --- | --- |
| PRAL/FBR sandbox token unavailable | Live reference APIs, live invoice validation and official sandbox scenario execution cannot be completed yet. | Await token/credentials from FBR portal or PRAL. | External dependency |
| Dashboard chart not fully verified | Chart implementation was started but final UI placement, build verification and browser testing are still pending. | Complete chart section and run frontend build/tests next session. | Next session |

Next Steps & Plan

| Planned Task | Assigned To | Target Date | Notes |
| --- | --- | --- | --- |
| Finish dashboard chart UI | Raees Tahir | 09/05/2026 | Complete Recharts section and verify /api/dashboard/charts output in frontend. |
| Add dashboard and invoice filters | Raees Tahir | 09/05/2026 | Date range, status and invoice type filters per Dev Guide. |
| Verify frontend build after chart/filter changes | Raees Tahir | 09/05/2026 | Run targeted tests and npm build. |
| Prepare documentation updates | Raees Tahir | 10/05/2026 | Local setup, environment variables, migrations and production checklist. |
| Live sandbox testing | Raees Tahir | Pending token | Run PRAL/FBR scenarios once sandbox token is available. |

Additional Notes / Client Communication

- Implementation is being done locally with mocked FBR responses because sandbox API credentials are not available yet.

- The documentation was rechecked and Prisma + PostgreSQL is confirmed as the required backend data architecture.

- Legacy database tables were removed only after confirming their data was already present in the new Invoice table.

Prepared by: Raees Tahir | AI Team | Date: 08/05/2026